## Outline
Project:Container passive house | Week | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | Effectiness*
| Week day | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | Total | %
Student: Lukas Abromas
Job
Floor plan groundfloor | Budget | 45 F: 2; 46 M: 3; 47 TH: 2 | 7
| Actual | 45 F: 3; 46 M: 2; 47 TH: 1 | 6
| Variance | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 14.29%
Personal Planing | Budget | 45 M: 2; 46 TH: 1 | 3
| Actual | 45 M: 2; 46 TH: 1 | 3
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Outline Section | Budget | 47 W: 4 | 4
| Actual | 47 W: 3 | 3
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 25%
Elevations | Budget | 47 M: 2; 47 T: 3 | 5
| Actual | 47 M: 2; 47 T: 2 | 4
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 20%
Site plan | Budget | 47 M: 2 | 2
| Actual | [21 empty] | 1 | bar: 47 M
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 50%
Shipping container placement | Budget | 45 F: 2; 46 W: 2 | 4
| Actual | 45 F: 2; 46 W: 1 | 3
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 25%
Renderings | Budget | 47 SU: 3 | 3
| Actual | 47 SU: 3 | 3
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
U value analysis | Budget | 45 SA: 5; 45 SU: 2 | 7
| Actual | 45 SA: 3; 45 SU: 2 | 5
| Variance | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 28.57%
Sound analysis | Budget | 45 SU: 2; 46 M: 2 | 4
| Actual | 45 SU: 2; 46 M: 4 | 6
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -50%
Instaltion analysis | Budget | 46 TH: 1; 46 F: 2 | 3
| Actual | 46 TH: 2; 46 F: 2 | 4
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -33.33%
Fire analysis | Budget | 46 SA: 1; 47 T: 2 | 3
| Actual | 46 SA: 2; 47 T: 2 | 4
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -33.33%
Desgin fee | Budget | 47 TH: 3 | 3
| Actual | 47 TH: 3 | 3
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Susesive calculaiton | Budget | 47 F: 3 | 3
| Actual | 47 F: 3 | 3
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Shipping container placement | Budget | 45 F: 4 | 4
| Actual | 45 F: 2 | 2
| Variance | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 50%
Consulation agreement | Budget | 45 F: 2 | 2
| Actual | 45 F: 2 | 2
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Structual analysis | Budget | 47 M: 4 | 4
| Actual | 47 M: 5 | 5
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -25%
Poster for outline | Budget | 47 SU: 2 | 2
| Actual | 47 SU: 2 | 2
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Revit modeling | Budget | 45 M: 4; 45 T: 3; 45 W: 4; 45 TH: 4; 45 SA: 5 | 20
| Actual | 45 M: 5; 45 T: 2; 45 W: 4; 45 TH: 5; 45 SA: 5 | 21
| Variance | -1 | 1 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -5%
80
* Effectinesson spent time: Effective <100% -less time spent than budgeted; Need for improvement >100% - exceeded budgeted hours.

## Scheme design
Project:Container passive house | Week | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | Effectiness*
| Week day | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | Total | %
Student: Lukas Abromas
Job
Personal Planning | Budget | 48 M: 3; 49 F: 2; 52 T: 2 | 7
| Actual | 48 M: 3; 49 F: 2; 52 T: 1 | 6
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 14.29%
Solving House | Budget | 49 TH: 4; 50 M: 3 | 7
| Actual | 49 TH: 5; 50 M: 2 | 7
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Column foundation K01_H5_EX_N01 | Budget | 48 T: 3; 48 W: 2 | 5
| Actual | 48 T: 3; 48 W: 2 | 5
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
External foundation K01_H5_EX_N02 | Budget | 48 M: 4; 48 T: 2; 52 W: 2 | 8
| Actual | 48 M: 3; 48 T: 2; 52 W: 2 | 7
| Variance | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12.5%
Container connection with column K01_H5_EX_N03 | Budget | 48 TH: 5; 48 F: 2; 52 M: 2 | 9
| Actual | 48 TH: 5; 48 F: 1; 52 M: 3 | 9
| Variance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
External wall + roof connection K01_H5_EX_N04 | Budget | 49 M: 5; 49 T: 4 | 9
| Actual | 49 M: 6; 49 T: 2 | 8
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11.11%
External wall corner l K01_H5_EX_N05 | Budget | 49 T: 2; 49 W: 2 | 4
| Actual | 49 T: 3; 49 W: 2 | 5
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -25%
Storey partition + wall K01_H5_EX_N06 | Budget | 49 W: 3; 49 TH: 2; 52 M: 2 | 7
| Actual | 49 W: 4; 49 TH: 2; 52 M: 2 | 8
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -14.29%
Roow window K01_H5_EX_N07 | Budget | 49 F: 3; 49 SA: 2; 51 M: 2; 52 W: 1 | 8
| Actual | 49 F: 4; 49 SA: 2; 52 W: 1 | 7
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12.5%
Skylight K01_H5_EX_N08 | Budget | 49 SA: 3; 49 SU: 4 | 7
| Actual | 49 SA: 3; 49 SU: 2 | 5
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 28.57%
Stair landing- storey partition K01_H5_EX_N09 | Budget | 48 SA: 3; 48 SU: 4; 51 TH: 2 | 9
| Actual | 48 SA: 3; 48 SU: 2; 51 TH: 1 | 6
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 33.33%
Wet room K01_H5_EX_N10 | Budget | 48 TH: 2; 48 F: 3 | 5
| Actual | 48 TH: 1; 48 F: 3 | 4
| Variance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 20%
Timber frame wall K01_H5_EX_N11 | Budget | 50 M: 2 | 2
| Actual | 50 M: 4 | 4
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | -100%
Ground floor plan upgraded | Budget | 49 F: 2; 50 T: 2 | 4
| Actual | 49 F: 0; 50 T: 2 | 2
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 50%
Ventilation calculations | Budget | 50 T: 3; 50 W: 6; 50 TH: 5 | 14
| Actual | 50 T: 5; 50 W: 6; 50 TH: 3 | 14
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Ventilation drawings | Budget | 50 TH: 3 | 3
| Actual | 50 TH: 2 | 2
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 33.33%
Cost calculations | Budget | 52 T: 3; 52 W: 3 | 6
| Actual | 52 T: 5; 52 W: 3 | 8
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | -2 | -33.33%
Elevation upgraded | Budget | 48 T: 2 | 2
| Actual | 48 T: 2 | 2
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
U value calculation | Budget | 50 F: 5 | 5
| Actual | 50 F: 2 | 2
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 60%
Section A-A | Budget | 51 M: 5; 51 T: 8; 51 W: 8; 51 TH: 4 | 25
| Actual | 51 M: 6; 51 T: 7; 51 W: 5; 51 TH: 2 | 20
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20%
Revit modeling | Budget | 48 W: 3; 48 SA: 5; 51 F: 4 | 12
| Actual | 48 W: 4; 48 SA: 2; 51 F: 5 | 11
| Variance | 0 | 0 | -1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8.333%
Bulding site plan | Budget | 49 M: 2 | 2
| Actual | 49 M: 2 | 2
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Fixing drawings | Budget | 51 F: 4; 52 TH: 5 | 9
| Actual | 51 F: 5; 52 TH: 3 | 8
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 11.11%
152
* Effectinesson spent time: Effective <100% -less time spent than budgeted; Need for improvement >100% - exceeded budgeted hours.

## Detail I
Project:Container passive house | Week | 53 | [6 empty] | Effectiness*
| Week day | M | T | W | TH | F | SA | SU | Total | %
Student: Lukas Abromas
Job
Ground floor plan | Budget | 3 | [6 empty] | 3
| Actual | 2 | [6 empty] | 2
| Variance | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 33.33%
Elevations | Budget | 1
| Actual | 1
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Section A-A | Budget |  | 2
| Actual |  | 2
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Foundaition plan | Budget |  |  | 5 |  |  |  |  | 5
| Actual |  |  | 5 |  |  |  |  | 5
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Sewer plan | Budget |  | 2 | 2 |  |  |  |  | 4
| Actual |  | 3 | 2 |  |  |  |  | 5
| Variance | 0 | -1 | 0 | 0 | 0 | 0 | 0 | -1 | -25%
Bulding permit | Budget |  |  |  | 1 |  |  |  | 1
| Actual |  |  |  | 1 |  |  |  | 1
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Site plan | Budget |  |  |  |  | 1 |  |  | 1
| Actual |  |  |  |  | 1 |  |  | 1
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Engergy frame | Budget |  |  |  | 5 | 10 | 5 |  | 20
| Actual |  |  |  | 6 | 9 | 2 |  | 17
| Variance | 0 | 0 | 0 | -1 | 1 | 3 | 0 | 3 | 15%
[8 empty] | Budget | 34
[7 empty] | Total: | Actual | 31
[8 empty] | Variance | 3 | 8.824%
* Effectinesson spent time: Effective <100% -less time spent than budgeted; Need for improvement >100% - exceeded budgeted hours.

## Detail II
Project:Groups Website | day | TH | F | SA | SU | M | Effectiness*
Developer: Lukas Abromas | [6 empty] | Total | %
Jobs:
Login - Registration | Budget | 5 |  |  |  |  | 5
| Actual | 4 |  |  |  |  | 4
| Variance | 1 | 0 | 0 | 0 | 0 | 1 | 20%
Admin- user page | Budget | 2 | 5 |  |  |  | 7
| Actual | 5 | 2 |  |  |  | 7
| Variance | -3 | 3 | 0 | 0 | 0 | 0 | 0%
Create groups | Budget |  | 3 |  |  |  | 3
| Actual |  | 3 |  |  |  | 3
| Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DELETE -UPDATE Groups | Budget |  |  |  | 6 |  | 6
| Actual |  |  |  | 8 |  | 8
| Variance | 0 | 0 | 0 | -2 | 0 | -2 | -33.33%
Edit users | Budget |  |  |  | 3 | 0 | 3
| Actual |  |  |  | 2 | 1 | 3
| Variance | 0 | 0 | 0 | 1 | -1 | 0 | 0%
25
* Effectinesson spent time: Effective <100% -less time spent than budgeted; Need for improvement >100% - exceeded budgeted hours.